## Planner
Research Edit4u Solutions
Timeline + Milestones Sheet (Gantt-ready)
Turn your scope into a practical milestone schedule with realistic sequencing.
Introduction Use this planner to turn your proposal into a practical schedule. List the major tasks, set realistic start and end points, mark the key deliverables, and shade the Gantt columns to show the work period. Update the sample rows to fit your own project.
No. | Task / Phase | Owner | Start | End | Status | Deliverable | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7
1 | Topic finalisation | Student | Week 1 | Week 1 | Planned | Approved topic | Narrow topic and context | bar: W1
2 | Literature scan | Student | Week 1 | Week 2 | Planned | Source base | Identify core references | bar: W1 to W2
3 | Problem statement + gap | Student | Week 2 | Week 2 | Planned | Core logic | Draft the issue and gap | bar: W2
4 | Objectives and RQs | Student + guide | Week 2 | Week 3 | Planned | Research focus | Align aim, objectives, and questions | bar: W2 to W3
5 | Methodology planning | Student | Week 3 | Week 4 | Planned | Methods map | Decide design, sample, tools, analysis | bar: W3 to W4
6 | Proposal drafting | Student | Week 4 | Week 5 | Planned | Draft document | Write proposal sections | bar: W4 to W5
7 | Supervisor review | Supervisor | Week 6 | Week 6 | Pending | Feedback notes | Receive comments and change requests | bar: W6
8 | Revision + final polish | Student | Week 6 | Week 7 | Pending | Final version | Format, QC, and final submission copy | bar: W6 to W7
How to use 1. Replace the sample tasks with your own milestones. 2. Update start/end labels. 3. Shade the week columns for the active task period. 4. Add more week columns if your project is longer. 5. Use the Status column to track progress before supervisor review and final submission.